## Iteration Estimated Effort
Roles:
Communicator - Sarah
Developers - Joshua, Mathewos, Scott, Sarah
SEO Specialist - Scott
Marketing Strategist - Scott
QA Engineer - Mathewos
Task Name: (Dependencies top to bottom) | [8 empty] | Sarah | Joshua | Mathewos | Scott | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
[5 empty] | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Requirements |  |  |  |  | 3 |  | 1
|  | Gather | Communicator | Sarah | 1 |  | 0 | [5 empty] | 0
|  | Analyze | Marketing Strategist | Scott | 1 |  | 0.5 |  |  |  |  | 0.5 | 0.5
|  | Specify | SEO Specialist | Scott | 1 |  | 0.5 |  |  |  |  | 0.5 | 0.5
| Client communication |  |  |  |  | 4 |  | 1
|  | Client Zoom Meeting | Communicator / Developers | Sarah | 4 |  | 1 |  |  |  |  | 1 | 1
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
Design & Build
Iteration 1: | Research and design |  |  |  |  | 5 |  | 3.25
|  | Research current website | Developers | All | 1 |  | 2 |  | 1 |  |  | 1 | 2
|  | Generate new page layout ideas | Developers | Scott, Sarah | 4 |  | 1.25 |  | 1 |  |  | 0.25 | 1.25
| Client Communication |  |  |  |  | 1 |  | 2.5
|  | Reach out to Lisa about attaining website information/pictures | Communicator | Sarah | 0.5 |  | 1.5 |  | 1.5 |  |  |  | 1.5
|  | Update client on current progress | Communicator |  | 0.5 |  | 1 |  | 1 |  |  |  | 1
| Development |  |  |  |  | 10 |  | 6
|  | Links to Social Media platforms | Developers | Sarah | 1 | 0.5 | 0.5 |  | 0.5 |  |  |  | 0.5
|  | Create page for Customer Reviews | Developers | Joshua, Mathewos | 3 |  | 1 |  |  |  | 1 |  | 1
|  | Add vendor links | Developers | Scott | 1 |  | 1 |  |  |  |  | 1 | 1
|  | Update store hours on regular site and square site | Developers | Joshua | 0.5 |  | 0.5 |  |  | 0.5 |  |  | 0.5
|  | Add new pictures and product information | Developers | Mathewos, Sarah | 3 |  | 2 |  | 1 |  | 1 |  | 2
|  | Test for bugs | QA Engineer | Mathewos | 1.5 |  | 1 |  |  |  | 1 |  | 1
| Iteration planning |  |  |  |  | 4 |  | 2
|  | Iteration 2 Planning | Developers | All | 4 |  | 2 |  | 1 |  |  | 1 | 2
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
Iteration 2:
| Client communication |  |  |  |  | 1 |  | 0
|  | Update client on current progress | Communicator | Sarah | 1 |  | 0 | [5 empty] | 0
|  | Show Lisa our changes and get feedback | Communicator | Sarah |  |  | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
| Development |  |  |  |  | 9.5 |  | 0
|  | Test for bugs | QA Engineer | Mathewos | 1.5 |  | 0 | [5 empty] | 0
|  | Look into rearranging layout of pages | Developers | All | 8 |  | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[6 empty] | 0 |  | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
Iteration 3:
[6 empty] | 0 |  | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[6 empty] | 0 |  | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
[6 empty] | 0 |  | 0
[7 empty] | 0 | [5 empty] | 0
[7 empty] | 0 | [5 empty] | 0
Total |  |  |  |  | 37.5 |  | 15.75 |  | 7 | 0.5 | 3 | 5.25 | 15.75